## Slide 1
Forward Deployed Engineer, RELEX | Week 6 | St. Louis, MO
RELEX Store Operations Recovery Plan — Northbridge Grocers
Week 6 Steering Committee — Data Integration, SSO, and the Path to Go-Live

## Slide 2: Where We Stand at Week 5
  Foundation is solid: kickoff complete, data feed contents agreed, store master data done, 25 tablets provisioned, product catalog issue root-caused
  Two decisions that were never actually finalized — how data lands in RELEX, how orders land back in SAP — are closed this week, pending your approval today
  SSO has three open items with Northbridge IT Security; a working session is scheduled this week — not yet a blocker, becomes one if it slips past Week 7
  No change to pilot scope: 25 stores, Iowa / Missouri, Fresh Produce, Bakery, Dairy, Frozen
On track for Week 12 — two decisions closed this week, need your sign-off today

## Slide 3: Data Integration Plan: Recommendation
Data In — Snowflake Read Access
  Read-only access to NB_RETAIL_CORE — covers sales, deliveries, stock movements, and product catalog in one integration
  Avoids the 6–8 week new-API approval process; Raj has already offered read-only access
  Rejected for pilot: SFTP-per-feed direct from SAP CAR / IS-Retail — six integration points instead of one, no material benefit
Orders Out — Existing SFTP Order Channel
  Flat-file drop into Z_ORD_INBOUND_PROC — 4-year-old production infrastructure already used for vendor PO confirmations
  Rejected for pilot: SAP IDoc (WHSORD03) — needs ~6 weeks basis + 2 weeks ABAP dev Marcus’s team doesn’t have until January
  Known limitation, flagged not hidden: orders tagged ORDER_TYPE=REGULAR for pilot; a proper order-type value is a fast-follow ask to Raj’s team
Both directions reuse infrastructure Northbridge already runs today

## Slide 4: Header 28pt
Content
Sub header

## Slide 5: Header 28pt
Content
Sub header

## Slide 6: Go / No-Go Criteria for Week 12
Measurable, Pre-Agreed Criteria
≥95%
SAP order acceptance rate across all 25 pilot stores
<2%
Unresolved product master conflicts after dedup, on a fresh extract
20 / 25
Store managers signing off tablet workflow as usable in daily operation
  SSO live for all store managers and category managers, with correct per-store access scoping
  Zero P1 data-quality incidents during the Week 11 parallel run
  Next status checkpoint: Week 8, same format, same audience
Every criterion is measurable — no “system feels ready” language